## Work Program_final
x
PROJECT WORK PROGRAM | [60 empty] | x
Project Schedule with Milestones and Time Table | [60 empty] | x
PROJECT : |  |  | PITX POS Tenant Sales Management Systems | [9 empty] | Gantt view | Weekly | [46 empty] | x
LOCATION : |  |  | 1 Kennedy Rd. Brgy. Tambo, Parañaque City | [9 empty] | Display | Actual | [46 empty] | x
UPDATED ON : |  |  | 2025-06-02 | [57 empty] | x
[13 empty] | BL0 |  |  |  | Running |  | as of MARCH 21, 2025 | [6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | x
NO |  |  | Activity or Milestones |  |  |  |  | Type | Description | Output | Responsible | Support | Duration (months) | Duration (days) | Plan Start Date | Plan End Date | Duration (months) | Duration (days) | Actual Start Date | Actual Finish Date | % of Completion | Predecessors | Amount | Date of Payment | Remarks | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24
|  |  | MODULE 1 Project Initiation & Requirement Gathering | [9 empty] | 1 | 26 | 2025-03-21 | 2025-04-16 | 1 | 5 | 2025-03-19 | 2025-03-24 | 100% | [39 empty] | x
L2 |  |  |  | 1.1 Project Initiation |  |  |  |  | Establish project structure, roles, & timeline | kick-off minutes |  |  | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 4 | 2025-03-19 | 2025-03-24 | 100% | - | [38 empty] | x
| L3 |  |  |  | 1.1.1 Kick-off Meeting |  |  | A | Align team & client on goals, scope, timelines |  |  |  | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 4 | 2025-03-19 | 2025-03-24 | 100% | - | [38 empty] | x
|  | L4 |  |  |  | 1.1.1.1 Schedule Kick-off Meeting |  | SA | Send invites to all parties | Calendar invite |  |  | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-19 | 2025-03-19 | 100% | 1.1.1.1 | [38 empty] | x
|  | L4 |  |  |  | 1.1.1.2 Prepare agenda & materials |  | SA | Prepared timeline overview |  |  |  | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-19 | 2025-03-19 | 100% | 1.1.1.2 | [38 empty] | x
|  | L4 |  |  |  | 1.1.1.3 Conduct the meeting |  | SA | Capture attendance and notes | Meeting log |  |  | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | 2025-03-21 | 100% | 1.1.1.3 | [38 empty] | x
|  | L4 |  |  |  | 1.1.1.4 Distribute minutes |  | SA | Email and folder upload |  |  |  | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 2 | 2025-03-21 | 2025-03-24 | 100% | 1.1.1.4
L2 |  |  |  | 1.2 Finalize Requirement |  |  |  | A | Finalize both PITX and POS provider requirements | Approved requirement documentation |  |  | 1 | 6 | 2025-03-24 | 2025-03-31 | 1 | 6 | 2025-03-21 | 2025-03-28 | 100% | [39 empty] | x
| L3 |  |  |  | 1.2.1 PITX Team requriements |  |  | SA | Identify and validate needs from PITX stakeholders | Reviewed checklist |  |  | 1 | 2 | 2025-03-24 | 2025-03-25 | 1 | 1 | 2025-03-21 | 2025-03-21 | 100% | [39 empty] | x
|  | L4 |  |  |  | 1.2.1.1 Interview key PITX stakeholders |  | SA | Understand reporting and tracking expectations | Notes from sessions | PPM,PFC | FIN,IT | 1 | 2 | 2025-03-24 | 2025-03-25 | 1 | 1 | 2025-03-21 | 2025-03-21 | 100% | 1.1.1.4 | [38 empty] | x
|  | L4 |  |  |  | 1.2.1.2 Document feature expectations |  | SA | Translate into feature list for backend/frontend dev | Feature list | PPM,PFC | FIN,IT | 1 | 2 | 2025-03-24 | 2025-03-25 | 1 | 1 | 2025-03-21 | 2025-03-21 | 100% | 1.2.2.1 | [38 empty] | x
|  | L4 |  |  |  | 1.2.1.3 Review & validate with PITX |  | SA | Confirm feasibility | Reviewed list | PPM,PFC | FIN,IT | 1 | 2 | 2025-03-24 | 2025-03-25 | 1 | 1 | 2025-03-21 | 2025-03-21 | 100% | 1.2.2.2
| L3 |  |  |  | 1.2.2 POS Provider Integration requirements |  |  |  | Gather integrtion requirement from POS provider | POS format validation doc |  |  | 1 | 5 | 2025-03-25 | 2025-03-31 | 1 | 6 | 2025-03-21 | 2025-03-28 | 100%
|  | L4 |  |  |  | 1.2.2.1 Confirm POS data format requirements |  | SA | Analyze transaction format from POS provider | Field mapping matrix | FIN,IT | PPM,PFC | 1 | 2 | 2025-03-25 | 2025-03-26 | 1 | 2 | 2025-03-21 | 2025-03-24 | 100% | 1.1.1.4
|  | L4 |  |  |  | 1.2.2.2 Validate with POS provider (if needed) |  | SA | Confirm consistency in batch upload structure | Validate format | FIN,IT | PPM,PFC | 1 | 2 | 2025-03-27 | 2025-03-28 | 1 | 1 | 2025-03-21 | 2025-03-21 | 100% | 1.2.2.1 | [38 empty] | x
|  | L4 |  |  |  | 1.2.2.3 Secure buy-in from POS software provider |  | SA | Confirm alignment and agreement with POS providers | Agreement/contract | FIN,IT | PPM,PFC | 1 | 3 | 2025-03-27 | 2025-03-31 | 1 | 1 | 2025-03-28 | 2025-03-28 | 100% | 1.2.2.2
L2 |  |  |  | 1.3 Requirement Sign-off |  |  |  |  | Finalize and approve MVP and UAT conditions | Signed scope and UAT checklist |  |  | 1 | 3 | 2025-03-27 | 2025-03-31 | 1 | 17 | 2025-03-28 | 2025-04-21 | 100% | [39 empty] | x
| L3 |  |  |  | 1.3.1 MVP Definition |  |  |  | Confirm features for MVP | MVP scope list |  |  | 1 | 2 | 2025-03-27 | 2025-03-28 | 1 | 17 | 2025-03-28 | 2025-04-21 | 100% | [39 empty] | x
|  | L4 |  |  |  | 1.3.1.1 List MVP Features |  |  | Prioritize by phase and value | MVP Draft | PPM | FIN,IT | 1 | 1 | 2025-03-27 | 2025-03-27 | 0 | 0 | 2025-03-29 | 2025-03-29 | 100% | 1.2.1.3, 1.2.2.3
|  | L4 |  |  |  | 1.3.1.2 Confirm feasibility withd Dev |  |  | Validate effort and scope | Dev approved list | PPM | FIN,IT | 1 | 1 | 2025-03-28 | 2025-03-28 | 1 | 1 | 2025-03-28 | 2025-03-28 | 100% | 1.3.1.1
| L3 |  |  |  | 1.3.2 UAT Criteria |  |  |  | Define conditions for UAT completion | UAT checklist |  |  | 0 | 0 | 2025-03-29 | 2025-03-29 | 1 | 16 | 2025-03-29 | 2025-04-21 | 100%
|  | L4 |  |  |  | 1.3.2.1 Draft UAT Success Criteria |  |  | Tie back to features and test cases | UAT Checklist Draft | PPM | FIN,IT | 0 | 0 | 2025-03-29 | 2025-03-29 | 0 | 0 | 2025-03-29 | 2025-03-29 | 100% | 1.3.1.1
| L3 |  |  |  | 1.3.3 Sign-off Review |  |  |  | Formalize scope & requirement sign-off | Signed document |  |  | 1 | 1 | 2025-03-30 | 2025-03-31 | 1 | 1 | 2025-04-21 | 2025-04-21 | 100%
|  | L4 |  |  |  | 1.3.3.1 Finalize requirements doc |  |  | Consolidated version for approval | Final version | PPM | FIN,IT | 1 | 1 | 2025-03-30 | 2025-03-31 | 1 | 1 | 2025-03-31 | 2025-03-31 | 100% | 1.3.1.2, 1.3.2.1
|  | L4 |  |  |  | 1.3.3.2 Conduct sign-off meeting |  |  | Review and client approval | Signed scope and UAT checklist | PPM | FIN,IT,COM | 1 | 1 | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-04-21 | 2025-04-21 | 100% | 1.3.3.1
L2 |  |  |  | 1.4 Resource and Environment Setup |  |  |  |  | Prepare and secure dev resources | Access credentials and infra ready |  |  | 1 | 3 | 2025-03-27 | 2025-03-31 | 2 | 47 | 2025-03-27 | 2025-05-30 | 100%
| L3 |  |  |  | 1.4.1 Secure Required Resources |  |  |  | Assign hardware, cloud, access credentials | Provisioned accounts |  |  | 1 | 3 | 2025-03-27 | 2025-03-31 | 2 | 47 | 2025-03-27 | 2025-05-30 | 100%
|  | L4 |  |  |  | 1.4.1.1 Create development server and database | Determine dev server requirement |  | Dev server | Access rights to dev environment | PPM,PTS,PFC |  | 1 | 1 | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-27 | 2025-03-27 | 100% | -
|  | L4 |  |  |  | 1.4.1.2 Secure required people resource |  |  | Dev team creation | Dev team | PPM | FIN | 1 | 2 | 2025-03-27 | 2025-03-28 | 1 | 7 | 2025-03-28 | 2025-04-07 | 100%
| L3 |  |  |  | 1.4.2 Setup Development Environment |  |  |  | Install required application, queue, config, etc. | Working local server |  |  | 1 | 1 | 2025-03-29 | 2025-03-31 | 2 | 45 | 2025-03-29 | 2025-05-30 | 100%
|  | L4 |  |  |  | 1.4.2.1 Insall dependencies |  |  | Configure required techstack | Installed Stack | PTS | PPM | 0 | 0 | 2025-03-29 | 2025-03-30 | 0 | 0 | 2025-03-29 | 2025-03-30 | 100% | 1.4.1.2
|  | L4 |  |  |  | 1.4.2.2 Configure environment Settings |  |  | queues, mail setup, etc. | Working dev environment | PTS | PPM,IT | 1 | 1 | 2025-03-30 | 2025-03-31 | 1 | 1 | 2025-03-29 | 2025-03-31 | 100% | 1.4.2.1
L2 |  |  |  | 1.5 Design Mockup UI Interface |  |  |  |  | Draft initial UI layout for stakeholder review | Prototype |  |  | 1 | 12 | 2025-04-01 | 2025-04-16 | 2 | 43 | 2025-04-02 | 2025-05-30 | 100%
| L3 |  |  |  | 1.5.1 Create Basic UI |  |  |  | Visualize dashboard | Draft wireframes |  |  | 1 | 9 | 2025-04-01 | 2025-04-12 | 1 | 14 | 2025-04-02 | 2025-04-21 | 100%
|  | L4 |  |  |  | 1.5.1.1 Idetify UI components |  |  | List required pages and elements | Component Checklist | PPM,PTS | FIN/IT/COM | 1 | 2 | 2025-04-01 | 2025-04-02 | 1 | 1 | 2025-04-02 | 2025-04-02 | 100% | 1.3.3.2
|  | L4 |  |  |  | 1.5.1.2 Design mockup screens |  |  | Create visual layout | Wireframe iamges | PPM,PTS | FIN/IT/COM | 1 | 7 | 2025-04-03 | 2025-04-12 | 1 | 8 | 2025-04-03 | 2025-04-14 | 100% | 1.5.1.1
|  | L4 |  |  |  | 1.5.1.3 Review mockup |  |  | Review and client approval | Approved UI Design | PPM,PTS | FIN/IT/COM | 1 | 3 | 2025-04-14 | 2025-04-16 | 1 | 6 | 2025-04-14 | 2025-04-21 | 100% | 1.5.1.2
|  |  | MODULE 2 Core System Development | [9 empty] | 2 | 60 | 2025-04-08 | 2025-06-07 | 2 | 40 | 2025-04-07 | 2025-05-30 | 100% | [39 empty] | x
L2 |  |  |  | 2.1 Core Development |  |  |  |  | Main phase involving backend logic, security, and testing | Functional backend and tested API |  |  | 2 | 44 | 2025-04-08 | 2025-06-07 | 2 | 40 | 2025-04-07 | 2025-05-30 | 100% | [39 empty] | x
| L3 |  |  |  | 2.1.1 Database Development |  |  |  | Design and implement TMS database schema | Finalized DB schema & migrations |  |  | 1 | 11 | 2025-04-08 | 2025-04-22 | 2 | 6 | 2025-04-07 | 2025-04-14 | 100%
|  | L4 |  |  |  | 2.1.1.1 Design Database schema and ERD |  |  | Plan entities, fields, and releationshps | ERD document | PFC | PPM | 1 | 3 | 2025-04-08 | 2025-04-10 | 1 | 4 | 2025-04-07 | 2025-04-10 | 100% | 1.3.3.2
|  | L4 |  |  |  | 2.1.1.2 Create Migration Files |  |  | Generate migration scripts | Migration files | PFC | PTS | 1 | 1 | 2025-04-11 | 2025-04-12 | 1 | 1 | 2025-04-11 | 2025-04-12 | 100% | 2.1.1.1
|  | L4 |  |  |  | 2.1.1.3 Foreign key constratinst implementation |  |  | Set relationships and optimize reads | Constraints and indexes | PFC | PPM | 1 | 1 | 2025-04-13 | 2025-04-14 | 1 | 1 | 2025-04-12 | 2025-04-14 | 100% | 2.1.1.2
|  | L4 |  |  |  | 2.1.1.4 Normalize fields and apply naming convention |  |  | Ensure clarity and scalability | Normalized table | PFC | PTS | 1 | 2 | 2025-04-15 | 2025-04-16 | 1 | 1 | 2025-04-15 | 2025-04-15 | 100% | 2.1.1.2
|  | L4 |  |  |  | 2.1.1.5 Peer review and schema |  |  | Validate DB structure | Approved schema | PFC | PPM,PTS | 1 | 2 | 2025-04-21 | 2025-04-22 | 1 | 1 | 2025-04-24 | 2025-04-24 | 100% | 2.1.1.3, 2.1.1.4
| L3 |  |  |  | 2.1.2 Security Implementation |  |  |  | Security Implementation |  |  |  | 1 | 5 | 2025-04-19 | 2025-04-25 | 1 | 5 | 2025-04-21 | 2025-04-25 | 100% | [39 empty] | x
|  | L4 |  |  |  | 2.1.2.1 Setup Authentication |  |  | Secure application via external config | Auth and permission logic implementation | PFC | PTS,PPM | 1 | 1 | 2025-04-19 | 2025-04-21 | 1 | 2 | 2025-04-21 | 2025-04-22 | 100% | 1.4.2.2 | [38 empty] | x
|  | L4 |  |  |  | 2.1.2.2 Configure RBAC |  |  | Token-based auth imlementation | Authentication middleware | PFC | PTS,PPM | 1 | 3 | 2025-04-21 | 2025-04-23 | 1 | 2 | 2025-04-22 | 2025-04-23 | 100% | 2.1.2.1 | [38 empty] | x
|  | L4 |  |  |  | 2.1.2.3 Enable data encryption for sensitive fields (if there's any) |  |  | Restrict per role access | RBAC matrix and policies | PFC | PTS,PPM | 1 | 2 | 2025-04-24 | 2025-04-25 | 1 | 2 | 2025-04-24 | 2025-04-25 | 100% | 2.1.2.1 | [38 empty] | x
|  | L4 |  |  |  | 2.1.2.4 Lock Config files |  |  | Secure app keys, tokens, and URLs | Encrypted fields | PTS | PFC | 1 | 1 | 2025-04-25 | 2025-04-25 | 1 | 2 | 2025-04-24 | 2025-04-25 | 100% | 2.1.2.3 | [38 empty] | x
| L3 |  |  |  | 2.1.3 POS Transaction Processing and Error Handling |  |  |  | Implement POS transaction pipeline and validation | API endpoint and queue logic |  |  | 1 | 18 | 2025-04-28 | 2025-05-21 | 1 | 8 | 2025-04-29 | 2025-05-08 | 100% | [39 empty] | x
|  | L4 |  |  |  | 2.1.3.1 Create transaction ingestion API |  |  | Accept and parse incoming payload | /api/v1/transactions - endpoint | PFC | PTS | 1 | 5 | 2025-04-28 | 2025-05-02 | 1 | 4 | 2025-04-29 | 2025-05-02 | 100% | 2.1.1.5 | [38 empty] | x
|  | L4 |  |  |  | 2.1.3.2 Build parser for POS text format |  |  | Convert fixed-width input into structured array | Parser service | PFC | - | 1 | 5 | 2025-05-05 | 2025-05-09 | 1 | 4 | 2025-05-05 | 2025-05-08 | 100% | 2.1.3.1 | [38 empty] | x
|  | L4 |  |  |  | 2.1.3.3 Implment job queues and processing logic |  |  | Use queue system for background jobs | Job class + worker setup | PFC | PTS | 1 | 5 | 2025-05-09 | 2025-05-15 | 1 | 4 | 2025-05-05 | 2025-05-08 | 100% | 2.1.3.2 | [38 empty] | x
|  | L4 |  |  |  | 2.1.3.4 Integrate error handling and retry mechanism |  |  | Catch failed jobs and retry mechanism | Error logs + retry strategy | PFC | - | 1 | 6 | 2025-05-14 | 2025-05-21 | 1 | 5 | 2025-05-12 | 2025-05-16 | 100% | 2.1.3.3 | [38 empty] | x
| L3 |  |  |  | 2.1.4 Sytem Testing and Deployment |  |  |  | Prepare fo UAT, execute tests, and deploy to staging | UAT results + staged system |  |  | 1 | 6 | 2025-05-20 | 2025-05-27 | 1 | 11 | 2025-05-16 | 2025-05-30 | 100% | [39 empty] | x
|  | L4 |  |  |  | 2.1.4.1 Write unit and integration tests |  |  | Cover key compents | Test comverage reports | PTS | PPM,IT | 1 | 3 | 2025-05-20 | 2025-05-22 | 1 | 2 | 2025-05-16 | 2025-05-19 | 100% | 2.1.3.4 | [38 empty] | x
|  | L4 |  |  |  | 2.1.4.2 Conduct internal testing and bug fixes |  |  | Ensure feature meets requirements | Test Log | PTS | PPM | 1 | 3 | 2025-05-23 | 2025-05-27 | 1 | 2 | 2025-05-20 | 2025-05-21 | 100% | 2.1.4.1
|  | L4 |  |  |  | 2.1.4.3 Prepare deployment checklist |  |  | Final validation before deployment | Deployment Checklist | PTS | - | 1 | 3 | 2025-05-28 | 2025-06-01 | 1 | 2 | 2025-05-23 | 2025-05-26 | 100% | 2.1.4.2
|  | L4 |  |  |  | 2.1.4.4 Deploy application to staging environment |  |  | Release application butil to LAN-based staging server | Staging development confirmation | PTS | - | 1 | 3 | 2025-06-02 | 2025-06-04 | 1 | 3 | 2025-05-27 | 2025-05-29 | 100% | 2.1.4.3
|  | L4 |  |  |  | 2.1.4.5 Conduct smoke testing in staging environment |  |  | Verify application is functional in staging environment | Smoke Test report | PTS | - | 1 | 2 | 2025-06-05 | 2025-06-07 | 1 | 3 | 2025-05-28 | 2025-05-30 | 100% | 2.1.4.4
|  |  | MODULE 3 Development and Integration | [5 empty] | Develop Supporting modules and connect core systems | Functional and Integrated Modules | PPM | PFC | 2 | 60 | 2025-05-28 | 2025-07-27 | 2 | 43 | 2025-05-28 | 2025-07-27 | 100% | [39 empty] | x
L2 |  |  |  | 3.1 Development and Intgration | [8 empty] | 2 | 43 | 2025-05-28 | 2025-07-27 | 2 | 43 | 2025-05-28 | 2025-07-27 | 100%
| L3 |  |  |  | 3.1 User Management Module |  |  |  | Define roles for tenant, accounting, admin | User access module |  |  | 1 | 14 | 2025-05-28 | 2025-06-16 | 1 | 7 | 2025-05-28 | 2025-06-05 | 100% | [39 empty] | x
|  | L4 |  |  |  | 3.1.1 Define user model and role structure |  |  | Define roles for tenant, accounting, admin, and finance | User and Role Schema | PFC,PTS | - | 1 | 2 | 2025-05-28 | 2025-05-29 | 1 | 3 | 2025-05-28 | 2025-05-30 | 100% | [39 empty] | x
|  | L4 |  |  |  | 3.1.2 Implment login, register and password login |  |  | Auth and password managment | Auth controller | PFC,PTS | PPM | 1 | 5 | 2025-05-30 | 2025-06-05 | 1 | 7 | 2025-05-28 | 2025-06-05 | 100% | 3.1.1
|  | L4 |  |  |  | 3.1.3 Integrate RBAC and PL packages |  |  | Role assignment and permission management | Role and Permission Table | PFC,PTS | PPM | 1 | 4 | 2025-06-06 | 2025-06-11 | 1 | 2 | 2025-06-04 | 2025-06-05 | 100% | 3.1.2
|  | L4 |  |  |  | 3.1.4 Build admin user Interface |  |  | CRUD and assignment screen for users | Admin user view | PFC,PTS | PPM | 1 | 6 | 2025-06-08 | 2025-06-16 | 1 | 8 | 2025-06-05 | 2025-06-16 | 100% | 3.1.3
| L3 |  |  |  | 3.2 Reporting Tools |  |  |  | Build summary reports | Reporting dashboard |  |  | 1 | 30 | 2025-06-16 | 2025-07-27 | 2 | 31 | 2025-06-13 | 2025-07-27 | 100% | [39 empty] | x
|  | L4 |  |  |  | 3.2.1 Define reporting requirements with PITX team |  |  | List reports needed by users | Reporting Specs | PFC,FIN/IT/COM | FIN | 1 | 2 | 2025-06-16 | 2025-06-17 | 1 | 10 | 2025-06-13 | 2025-06-26 | 100% | [39 empty] | x
|  | L4 |  |  |  | 3.2.2 Build report views and endpoints |  |  | Summary, CMSR, and POS transaction reports | Report Endpoints | PFC | PPM,PTS,FIN/IT/COM | 1 | 5 | 2025-06-17 | 2025-06-23 | 1 | 25 | 2025-06-13 | 2025-07-17 | 100% | 3.2.1 | [38 empty] | x
|  | L4 |  |  |  | 3.2.3 Add filtes and export options |  |  | Filtesr by tenant, date, POS, etc | Export-enabled reports | PFC | PPM,PTS,FIN/IT/COM | 1 | 4 | 2025-06-24 | 2025-06-28 | 2 | 31 | 2025-06-13 | 2025-07-27 | 100% | 3.2.2 | [38 empty] | x
| L3 |  |  |  | 3.3 Real-Time Data Synchronization & Middleware |  |  |  | Middleware for processing incoming POS data | Real-time middleware |  |  | 1 | 20 | 2025-06-29 | 2025-07-27 | 1 | 24 | 2025-06-16 | 2025-07-17 | 100% | [39 empty] | x
|  | L4 |  |  |  | 3.3.1 Design data flow and processing engine |  |  | Input validation, transform, and queue jobs | Flow diagram and services | PPM,IT | PFC | 1 | 5 | 2025-06-29 | 2025-07-05 | 1 | 5 | 2025-06-30 | 2025-07-04 | 100%
|  | L4 |  |  |  | 3.3.2 Implement retry and fallback logic |  |  | Error handling and retries | Retry config | PPM,IT | PFC | 1 | 8 | 2025-07-06 | 2025-07-16 | 1 | 4 | 2025-06-16 | 2025-06-19 | 100% | 3.3.1
|  | L4 |  |  |  | 3.3.3 Validate data consistency and processing logs |  |  | Ensure reliability and logs | Validation reports | PPM,IT | PFC | 1 | 4 | 2025-07-17 | 2025-07-22 | 1 | 2 | 2025-07-16 | 2025-07-17 | 100% | 3.3.2
|  | L4 |  |  |  | 3.3.4 Conduct Middleware performance test |  |  | Load test real-time queue and middleware | Load test report | PPM,IT | PFC | 1 | 4 | 2025-07-22 | 2025-07-27 | 1 | 4 | 2025-07-21 | 2025-07-24 | 100% | 3.3.3
|  |  | MODULE 4 Deployment and Support | [5 empty] | Deploy to production, train users, finalize support | Go-live and transitioned operations | PPM | CPM | 2 | 47 | 2025-07-17 | 2025-09-02 | 0 | 0 |  |  | 100% | [39 empty] | x
L2 |  |  |  | 4.1 Production Depolyment |  |  |  |  | Final preparatoin and launch to production | Live system |  |  | 1 | 16 | 2025-07-17 | 2025-08-02 | 1 | 4 | 2025-07-17 | 2025-07-22 | 100% | [39 empty] | x
| L3 |  |  |  | 4.1.1 Final System Testing in Production |  |  |  | Verify all systems post-deployments | Test results and logs |  |  | 1 | 6 | 2025-07-17 | 2025-07-23 | 1 | 4 | 2025-07-17 | 2025-07-22 | 100%
|  | L4 |  |  |  | 4.1.1.1 Execute smoke tests |  |  | Validate application in live state | Smoke test log | PTS | - | 1 | 4 | 2025-07-17 | 2025-07-21 | 1 | 3 | 2025-07-17 | 2025-07-21 | 100%
|  | L4 |  |  |  | 4.1.2.1 Validate Integrations |  |  | Confirm middleware/data flow | Integration test report | PTS | - | 1 | 1 | 2025-07-22 | 2025-07-23 | 1 | 19 | 2025-08-17 | 2025-07-22 | 100% | 4.1.1.1
| L3 |  |  |  | 4.1.2 Production Database Migration and Initialization |  |  |  | Final DB copy and seeding | Live production DB |  |  | 1 | 3 | 2025-07-24 | 2025-07-27 | 0 | 0 |  |  | 100% | [39 empty] | x
|  | L4 |  |  |  | 4.1.2.1 Migrate final schema/data |  |  | Move from stating to prod | Migrated data sets | PTS | - | 1 | 1 | 2025-07-24 | 2025-07-25 | 1 | 5 | 2025-07-21 | 2025-07-25 | 100% | 4.1.1.1
|  | L4 |  |  |  | 4.1.2.2 Intialize system with latest configs |  |  | Apply live creadentials and environment settings | Running app | PTS | - | 1 | 2 | 2025-07-25 | 2025-07-27 | 1 | 1 | 2025-07-25 | 2025-07-27 | 100%
| L3 |  |  |  | 4.1.3 Security and Performance Optimization |  |  |  | Harden the fune system for live ops | Optimization logs |  |  | 1 | 5 | 2025-07-28 | 2025-08-02 | 0 | 0 |  |  | 100%
|  | L4 |  |  |  | 4.1.3.1 Apply security patches |  |  | Ensure config and server and config updates | Updated system | PTS |  | 1 | 1 | 2025-07-28 | 2025-07-29 | 1 | 3 | 2025-07-28 | 2025-07-30 | 100% | 4.1.2.2
|  | L4 |  |  |  | 4.1.3.2 Tune queue and database performance |  |  | Optimize queue and indexing | Performance log | PTS |  | 1 | 3 | 2025-07-30 | 2025-08-02 | 1 | 3 | 2025-07-30 | 2025-08-02 | 100%
L2 |  |  |  | 4.2 User training |  |  |  |  | Tranin all user types before final handover | Training attendance logs | PPM |  | 1 | 21 | 2025-08-06 | 2025-08-27 | 1 | 16 | 2025-08-06 | 2025-08-27 | 100% | [39 empty] | x
| L3 |  |  |  | 4.2.1 Admin and IT Support Training |  |  |  | Train technical team on system | Admin training log | PTS |  | 1 | 4 | 2025-08-06 | 2025-08-10 | 1 | 3 | 2025-08-06 | 2025-08-10 | 100% | [39 empty] | x
|  | L4 |  |  |  | 4.2.1.1 Walkthrough system admin tools |  |  | Interface, logs, queue handling | Support Playbook | PTS |  | 1 | 1 | 2025-08-06 | 2025-08-07 | 1 | 2 | 2025-08-06 | 2025-08-07 | 100% | [39 empty] | x
|  | L4 |  |  |  | 4.2.1.2 Train on issue escalation and backup |  |  | Support process | Escalation Matrix | PTS |  | 1 | 2 | 2025-08-08 | 2025-08-10 | 1 | 1 | 2025-08-08 | 2025-08-10 | 100% | 4.2.1.1
| L3 |  |  |  | 4.2.2 Tenant and Operations training |  |  |  | Train end users (Accounting/finance/ops) | User Training Records |  |  | 1 | 4 | 2025-08-11 | 2025-08-15 | 1 | 5 | 2025-08-11 | 2025-08-15 | 100%
|  | L4 |  |  |  | 4.2.2.1 Preparing training materials |  |  | Customized guidelines for tenant usage | Tenant specific handouts | PPM | FIN/IT/COM | 1 | 1 | 2025-08-11 | 2025-08-12 | 1 | 2 | 2025-08-11 | 2025-08-12 | 100%
|  | L4 |  |  |  | 4.2.2.2 Conduct training sessions |  |  | Deliver training to operations/account staff | Attendance record | PPM | FIN/IT/COM | 1 | 2 | 2025-08-13 | 2025-08-15 | 1 | 3 | 2025-08-13 | 2025-08-15 | 100% | 4.2.2.1
| L3 |  |  |  | 4.2.3 Final Documentation and Knowledge Transfer |  |  |  | Povide user guides and KBs [Knowledge Base] | Training Kit and Docs |  |  | 1 | 8 | 2025-08-19 | 2025-08-27 | 1 | 7 | 2025-08-19 | 2025-08-27 | 100%
|  | L4 |  |  |  | 4.2.3.1 Compile Training documentation |  |  | Collect and organize all material and slides | Training kit | PPM | FIN/IT/COM | 1 | 1 | 2025-08-19 | 2025-08-20 | 1 | 2 | 2025-08-19 | 2025-08-20 | 100%
|  | L4 |  |  |  | 4.2.3.2 Transfer Knowledge to client team |  |  | Walkthrough of SOPs and escallation paths | Knowledge base index | PPM | FIN/IT/COM | 1 | 2 | 2025-08-21 | 2025-08-23 | 1 | 2 | 2025-08-21 | 2025-08-23 | 100% | 4.2.3.1
|  | L4 |  |  |  | 4.2.3.3 Upload documentation to shared drive |  |  | Ensure all users can access lates documentation | Accessible training folder | PPM | FIN/IT/COM | 1 | 1 | 2025-08-24 | 2025-08-25 | 1 | 1 | 2025-08-24 | 2025-08-25 | 100% | 4.2.3.2
|  | L4 |  |  |  | 4.2.3.4 Validate uploaded documents with client |  |  | Confirm all files are available and complete | Validated checklist | PPM | FIN/IT/COM | 1 | 1 | 2025-08-26 | 2025-08-27 | 1 | 2 | 2025-08-26 | 2025-08-27 | 100% | 4.2.3.3
L2 |  |  |  | 4.3 Final Project Handover and closure |  |  |  |  | Confirm service levels and finalize sign-off | Project closure kit |  |  | 1 | 5 | 2025-08-28 | 2025-09-02 | 1 | 3 | 2025-08-28 | 2025-09-01 | 100% | [39 empty] | x
| L3 |  |  |  | 4.3.1 System Handover Meeting |  |  |  | Review delivery checklist | Handover notes |  |  | 1 | 1 | 2025-08-28 | 2025-08-29 | 1 | 2 | 2025-08-28 | 2025-08-29 | 100% | [39 empty] | x
|  | L4 |  |  |  | 4.3.1.1 Conduct Handober Meeting |  |  |  |  | PPM | FIN/IT/COM | 1 | 1 | 2025-08-28 | 2025-08-29 | 1 | 2 | 2025-08-28 | 2025-08-29 | 100%
| L3 |  |  |  | 4.3.2 SLA and Support Agreement Finalization |  |  |  | Review and sign SLAs and warranties | Signed SLA doc |  |  | 1 | 2 | 2025-08-29 | 2025-08-31 | 1 | 1 | 2025-08-29 | 2025-08-31 | 100%
|  | L4 |  |  |  | 4.3.2.1 Draft SLA with stakeholders |  |  | Prepare draft SLA based on project scope | SLA Draft | PPM,FIN | FIN/IT/COM | 0 | 0 | 2025-08-29 | 2025-08-29 | 1 | 1 | 2025-08-29 | 2025-08-29 | 100%
|  | L4 |  |  |  | 4.3.2.2 Review SLA with stakeholders |  |  | Align SLA terms and warranty clauses | Reviewed SLA | PPM,FIN | FIN/IT/COM | 1 | 1 | 2025-08-30 | 2025-08-31 | 0 | 0 | 2025-08-30 | 2025-08-31 | 100% | 4.3.2.1
| L3 |  |  |  | 4.3.3 Post-Deployment Review and Sign-off |  |  |  | Conduct final walkthrough and evaluation | Signed project closure |  |  | 1 | 1 | 2025-09-01 | 2025-09-02 | 1 | 1 | 2025-09-01 | 2025-09-01 | 100%
|  | L4 |  |  |  | 4.3.3.1 Conduct closure review meeting |  |  | Recap delivery, training, and open issues | Meeting minutes | PPM,FIN | FIN/IT/COM | 0 | 0 | 2025-09-01 | 2025-09-01 | 1 | 1 | 2025-09-01 | 2025-09-01 | 100% | [39 empty] | x
|  | L4 |  |  |  | 4.3.3.2 Get final sign-off from client |  |  | Client foncirms project closure and delivery | Signed clsure document | PPM,FIN | FIN/IT/COM | 0 | 0 | 2025-09-02 | 2025-09-02 | [5 empty] | 4.3.3.1 | [38 empty] | x
x
x |  |  | LEGEND: (for Columns A to M, Y to AC) | [11 empty] | LEGEND: (for Columns O to W)
|  |  | L1 | PHASE | [11 empty] | Cells with values (not formula)
|  |  | L2 | ACTIVITY |  |  | conditional formatting will trigger inputs on Column A | [8 empty] | Cells with formulas
|  |  | L3 | SUB-ACTIVITY |  |  | conditional formatting will trigger inputs on Column B | [8 empty] | Blank cells
|  |  | L4 | DETAILED ACTIVITY |  |  | conditional formatting will trigger inputs on Column C

## Work Program_old (hidden)
x
|  |  | PROJECT WORK PROGRAM - TEMPLATE | [62 empty] | 0 | x
|  |  | Project Schedule with Milestones and Time Table | [63 empty] | x
PROJECT : |  |  | [PROJECT NAME] | [13 empty] | Gantt view | Monthly | [48 empty] | x
LOCATION : |  |  | [ADDRESS], [CITY] | [13 empty] | Display | Actual | [48 empty] | x
UPDATED ON : |  |  | 2023-05-15 | [63 empty] | x
[13 empty] | BL0 |  |  |  | BL1 |  |  |  | Running | as of January 10, 2025 | [9 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | x
NO |  |  | Activity or Milestones |  |  |  |  | Type | Description | Output | Responsible | Support | Duration (days) | Plan Start | Plan Finish |  | Duration (days) | Plan Start Date | Plan End Date |  | Duration (days) | Actual Start Date | Actual Finish Date |  | Remarks | % of Completion | Predecessors | Amount | Date of Payment | Remarks |  | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31
1 |  |  | INITIATION PHASE | [13 empty] | 455 | 2023-05-01 | 2024-07-29 | [47 empty] | x
1.1 |  |  |  | Sourcing Potential Land for Development |  |  |  |  | Understand market conditions, demand drivers, and potential risks, enabling the company to position itself effectively in the market. Then identifying and selecting potential properties that meet specific criteria for investment, development, or sale. | Property Shortlist | BD
1.2 |  |  |  | Deliberation to Go or No Go for Development |  |  |  |  | Present properties during EXECOM and decide if Go or No-Go | Term Sheet/ LOI | BD
1.3 |  |  |  | High-level Legal and Technical Due Diligence |  |  |  |  | Perform a hi-level review of the legal documents of the property ie Title , Ownership, Corporations etc. | Validated Title | Legal |  | 669 | 2023-06-15 | 2026-01-06 |  | 45 | 2023-06-15 | 2023-08-16 |  | 669 | 2023-06-15 | 2026-01-06 |  |  | #REF! | [40 empty] | x
1.4 |  |  |  | Conduct Feasibility Study |  |  |  |  | Perform the FS study which include the Market Scan, Product Study, Hi-level Financial Model, Stakeholders map and Risk register. Include high-level work program Arch'l Concept Design (if needed) | Feasibility Study | PD |  | 1 | 2023-06-15 | 2023-06-15 |  | 1 | 2023-06-15 | 2023-06-15 |  | 1 | 2023-06-15 | 2023-06-15 |  |  | 100% | [40 empty] | x
1.5 |  |  |  | Submit Proposal
1.6 |  |  |  | Negotiation & Awarding |  |  |  | M |  | DOAS | BD / President |  | 412 | 2023-05-01 | 2024-11-26 |  | 455 | 2023-05-01 | 2024-07-29 |  | 430 | 2023-05-01 | 2024-12-20 | [43 empty] | x
1.7 |  |  |  | Contract Closing
| 1.7.1 |  |  |  | Joint Venture Agreement |  |  | S |  |  | BD / President |  | 153 | 2023-05-01 | 2023-10-01 |  | 30 | 2023-05-01 | 2023-06-09 |  | 110 | 2023-05-01 | 2023-10-01 |  |  |  | Title & Tech Description | [39 empty] | x
[6 empty] | JVA Re-Execution to Reflect New Zonal Value |  |  |  |  | BD | Legal | 1 | [7 empty] | 15 | 2024-05-10 | 2024-05-30 | [43 empty] | x
[6 empty] | PFSS Re-Execution to Reflect New Zonal Value |  |  |  |  | BD | Legal | [8 empty] | 15 | 2024-05-10 | 2024-05-30 | [43 empty] | x
| 1.7.2 |  |  |  | Incorporation of JV Company | [5 empty] | BD | Legal | 132 | 2023-10-01 | 2024-02-10 |  | 90 | 2023-06-09 | 2023-10-12 |  | 95 | 2023-10-01 | 2024-02-10 |  | Actual start date from JV signing |  | Title & Tech Description | [39 empty] | x
| 1.7.3 |  |  |  | Title Exchange Process | [5 empty] | BD |  | 150 | 2024-02-10 | 2024-09-05 |  | 150 | 2023-10-12 | 2024-05-08 |  | 89 | 2024-05-30 | 2024-10-01 |  |  |  | Title & Tech Description |  |  | confirmed measures with DHSUD on undertaking of title transfer for annotation of MDDR. Proceed with TLS as scheduled | [36 empty] | x
[6 empty] | Increase in Capital Stock |  |  |  |  | BD | Legal |  |  |  |  | 30 | 2023-10-12 | 2023-11-22 |  | 60 | 2024-05-30 | 2024-08-21 |  |  |  | Title & Tech Description |  |  | for PDC issuance to JV partner; ongoing with docs routing for increase in capital stock | [36 empty] | x
[6 empty] | Tax Free Exchange |  |  |  |  | BD | Legal |  |  |  |  | 60 | 2023-10-12 | 2024-01-03 |  | 30 | 2024-08-21 | 2024-10-01 |  |  |  | Title & Tech Description |  |  | Ongoing routing of documents for submission for BIR | [36 empty] | x
[6 empty] | eCAR |  |  |  |  | BD | Legal |  |  |  |  | 60 | 2023-10-12 | 2024-01-03 |  | 30 |  | 1900-02-08 |  |  |  | Title & Tech Description | [39 empty] | x
| 1.7.4 |  |  |  | Title Transfer from VMI to JVCo | [5 empty] | BD |  | 30 | 2024-09-05 | 2024-10-16 |  | 30 | 2024-05-08 | 2024-06-18 |  | 30 | 2024-10-01 | 2024-11-11 |  | Can be undertaking |  | Title & Tech Description | [39 empty] | x
| 1.7.5 |  |  |  | Tax Dec Transfer from VMI to JVCo | [5 empty] | BD |  | 30 | 2024-10-16 | 2024-11-26 |  | 30 | 2024-06-18 | 2024-07-29 |  | 30 | 2024-11-11 | 2024-12-20 |  |  |  | Title & Tech Description | [39 empty] | x
2 |  |  | PLANNING PHASE | [10 empty] | 0 | 2025-04-02 |  | 699 | 2023-04-19 | 2025-03-18 |  | 993 | 2023-04-19 | 2026-01-06 | [43 empty] | x
2.1 |  |  |  | Develop Project Charter |  |  |  |  | Includes Concept design, Schedule, Project Cost, Market, Sales, Risk Register, Stakeholders Map | Project Charter | PD
2.2 |  |  |  | Conduct Pre-Engineering Studies |  |  |  |  | Perform pre-engineering studies and information gathering such Lot Survey, Soil Investigation, Topography , Flood Study, Traffic Study etc. as needed, depending on the location of the property site. All of these information will be needed by the Design Consultants to complete the Deisgn Work . | Lot Survey, Soil Investigation, Topographic Survey etc |  |  | 174 | 2023-07-21 | 2024-03-20 |  | 57 | 2023-07-12 | 2023-09-28 |  | 181 | 2023-07-12 | 2024-03-20 | [43 empty] | x
| 2.2.1 |  |  |  | Lot Survey | [5 empty] | PD | D&C | 50 | 2023-07-21 | 2023-09-28 |  | 57 | 2023-07-12 | 2023-09-28 |  | 57 | 2023-07-12 | 2023-09-28 |  |  |  | Title & Tech Description |  |  | done | [36 empty] | x
| 2.2.2 |  |  |  | Topographic Survey | [5 empty] | PD | D&C | 50 | 2023-07-21 | 2023-09-28 |  | 57 | 2023-07-12 | 2023-09-28 |  | 57 | 2023-07-12 | 2023-09-28 |  |  |  | Title & Tech Description |  |  | done | [36 empty] | x
| 2.2.3 |  |  |  | Soil Investigation | [5 empty] | PD | D&C | 25 | 2024-02-15 | 2024-03-20 |  | -32384 | 2024-02-15 | 0 |  | 25 | 2024-02-15 | 2024-03-20 |  |  |  | Title & Tech Description |  |  | confirm actual date of submission of complete samples | [36 empty] | x
| 2.2.4 |  |  |  | VRT ? | [5 empty] | PD | D&C | 50 | 2023-07-21 | 2023-09-28 |  | 57 | 2023-07-12 | 2023-09-28 |  | 57 | 2023-07-12 | 2023-09-28 |  |  |  | Title & Tech Description |  |  | done | [36 empty] | x
2.3 |  |  |  | Develop Project Design |  |  |  |  | Develop the Design of the project in multiple stages - Concept Dwg, Schematic Dwg and eventually the Construction Dwg . Every stages of the Design shall be collaboratively discussed altogether by multiple disicplines to make sure that all trades are properly coordinated which shall be presented to Management for approval every stages . | CD, SD, FCD |  |  | 270 | 2023-04-19 | 2024-04-30 |  | 270 | 2023-04-19 | 2024-04-30 |  | 351 | 2023-04-19 | 2024-08-21 | [43 empty] | x
| 2.3.1 |  |  |  | Masterplan & Concept Drawings |  |  |  | Base on the Product , market and pricing study done in FS , the Concept Dwg (CD) which include Unit Floor Plan & Massing of the Bldg shall be developed by the Archt together with the PD & Design team to be presented to the Management for approval. At this stage, the Design Criteria shall be finalized incorporating the FS requirements and the CD which will then be used for the development of the Schematic Dwg up to Construction Dwg. |  | C&D | PD | 213 | 2023-04-19 | 2024-02-09 |  | 213 | 2023-04-19 | 2024-02-09 |  | 213 | 2023-04-19 | 2024-02-09 | 296 | Running from first submission; signed off Feb 9 2024 | 100% | Design Criteria | [39 empty] | x
| 2.3.2 |  |  |  | Schematic Drawings 1 |  |  |  | For Arch'l , SD dwgts are the Typical Floor Units , Ground Floor and the Podium Level. For Structural, the Typical Floor Framing and the indicative sizes of the Elements ie Columns, Shearwalls, Slab and Corewalls. For MEPF, the Typical Units and Hallways. |  | C&D | PD | 50 | 2024-02-09 | 2024-04-18 |  | 50 | 2024-02-09 | 2024-04-18 |  | 50 | 2024-02-09 | 2024-04-18 | 69 | Feb 9 2024 Kick Off | 100% | Design Concept | [39 empty] | x
| 2.3.3 |  |  |  | Schematic Drawings 2 | [5 empty] | C&D | PD | 9 | 2024-04-18 | 2024-04-30 |  | 9 | 2024-04-18 | 2024-04-30 |  | 90 | 2024-04-18 | 2024-08-21 | 125 | needed for major permit |  | SD1 |  |  | ongoing revision of podium | [36 empty] | x
| 2.3.4 |  |  |  | Construction Drawing & Mat'l Spec'n | [5 empty] | C&D | PD | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | SD2 | [39 empty] | x
2.5 |  |  |  | Secure Regulatory, Legal & Permits | [8 empty] | 108 | 2024-02-10 | 2024-07-10 |  | 195 | 2023-10-12 | 2024-07-10 |  | 203 | 2024-02-10 | 2024-11-20 | [43 empty] | x
| 2.5.1 |  |  |  | Cleanup of Title |  |  |  | Title Segration, Transfer Tax, CGT, eCAR, Transfer of Title | Title | Legal |  | 90 | 2024-02-10 | 2024-06-13 |  | 90 | 2023-10-12 | 2024-02-14 |  | 90 | 2024-02-10 | 2024-06-13 |  | simultaneous with title exchange | [41 empty] | x
| 2.5.2 |  |  |  | CAAP Clearance (if applicable) |  |  |  |  | CAAP Clearance |  |  | 60 | 2024-04-18 | 2024-07-10 |  | 60 | 2024-04-18 | 2024-07-10 |  | 34 | 2024-04-18 | 2024-06-04 |  | secured |  | Conceptual Design |  |  | Secured | [36 empty] | x
| 2.5.3 |  |  |  | EGAR | [7 empty] | 30 | 2024-04-18 | 2024-05-29 |  | 30 | 2024-04-18 | 2024-05-29 |  | 80 | 2024-04-18 | 2024-08-07 |  | submitted with ECC |  | Environmental Impact Assessment | [39 empty] | x
| 2.5.4 |  |  |  | ECC |  |  |  |  | ECC Permit |  |  | 85 | 2024-02-26 | 2024-06-21 |  | 85 | 2024-02-26 | 2024-06-21 |  | 268 | 2024-02-26 | 2024-11-20 |  | pending release, with draft |  | SD1, etc. |  |  | Public Hearing OCT 18; Submit by DEC 2024 | [36 empty] | x
2.6 |  |  |  | Develop Marketing Plan | [5 empty] | Marketing Plan | Mktg |  | 88 | 2024-05-01 | 2024-08-30 |  | 100 | 2024-05-01 | 2024-08-09 |  | 98 | 2024-05-01 | 2024-09-15 |  | for update from Yana | 100% | 6 Mos before launch | [39 empty] | x
| 2.6.1 |  |  |  | Prepare Marketing Strategy |  |  |  | Develop the Marketing Strategy base on the Mkt Scan & Competitive Analasys, Target Market & Customer Personification, Market Positioning & RTB's, Marketing Strategy (Launch & Sustaining Plan) etc. | Marketing Strategy | Mktg |  | 65 | 2024-05-01 | 2024-07-30 |  | 60 | 2024-05-01 | 2024-07-23 |  | 88 | 2024-05-01 | 2024-08-30 |  |  | 100% | 6 Mos before launch |  |  | Ongoing | [36 empty] | x
| 2.6.2 |  |  |  | Prepare Marketing Collaterals |  |  |  | Digital and Physical | Maktg Collaterals | Mktg |  | 34 | 2024-07-01 | 2024-08-15 |  | 30 | 2024-07-01 | 2024-08-09 |  | 45 | 2024-07-01 | 2024-08-30 | [6 empty] | digital & hard copies
| 2.6.3 |  |  |  |  | Renders |  |  |  | Website | Mktg |  | 35 | 2024-07-15 | 2024-08-30 | [5 empty] | 32 | 2024-08-01 | 2024-09-15 |  | ongoing for finalization
| 2.6.4 |  |  |  |  | Digital Materials |  |  |  | Website | Mktg |  | 35 | 2024-07-15 | 2024-08-30 | [5 empty] | 22 | 2024-08-01 | 2024-08-30
2.7 |  |  |  | Develop Sales Plan | [5 empty] | Sales Plan | Sales |  | 23 | 2024-07-01 | 2024-07-31 |  | 60 | 2024-07-01 | 2024-08-30 |  | 45 | 2024-07-01 | 2024-08-30 |  |  | 100% | [40 empty] | x
| 2.7.1 |  |  |  | Sales Strategy Plan |  |  |  | Define the Sales Strategy which include Sales Mo Target, Budget, Pricing Tiering, Blolcking , Payment Terms, Discounting Matrix, Commission & Incentive Structure, Buyer's Promo Matrix. | Sales Strategy | Sales |  | 23 | 2024-07-01 | 2024-07-31 |  | 30 | 2024-07-01 | 2024-08-30 |  | 45 | 2024-07-01 | 2024-08-30 |  |  | 100% | 6 Mos before launch |  |  | Delayed - included in bplan | [36 empty] | x
| 2.7.2 |  |  |  | Sales Plantilla and Training Plan |  |  |  | Present the Sales Organization Structure & Plantilla for whole project with Budget which include the Training Plan (Calendar Plan, Curricullum) | Sales Workforce Plan | Sales | HR | 23 | 2024-07-01 | 2024-07-31 |  |  | 2024-07-01 | 2024-07-31 |  | 23 | 2024-07-01 | 2024-07-31 |  |  | 100% | 6 Mos before launch |  |  | Done - onboarding already | [36 empty] | x
| 2.7.3 |  |  |  | Sales Policies and Procedures |  |  |  | Sales Policies and Procedures for , Promos, Discounting, Payment, Brokers' Commission etc. | Sales Manual | Sales |  | 0 | [7 empty] | 0 |  |  |  |  | 100% | 6 Mos before launch |  |  | Existing | [36 empty] | x
9 |  |  |  | Sales Documentation Plan | [6 empty] | Sales Admin |  | 0 | 0 | 0 |  | 156 | 2024-05-01 | 2024-10-04 |  | 110 | 2024-05-01 | 2024-10-01 | [6 empty] | Existing | [36 empty] | x
| 9.1 |  |  |  | Prepare the Std Buyers' Documentations |  |  |  | Prepare all Buyer's Documents required for selling which include Customer Registration Form, Data Privacy Form, Buyer Information Sheet, Master Deed, Declaration of Restriction, Reservation Agreement, Contract to Sell, DOAS, and other standard Letters (Welcome & Thank You ) | Customer Registration Form, Data Privacy Form, Buyer Information Sheet, Master Deed, Declaration of Restriction, Reservation Agreement, Contract to Sell, DOAS | Sales Admin |  | 0 |  |  |  |  | 2024-05-01 | 2024-05-01 |  | 1 | 2024-05-01 | 2024-05-01 |  |  |  | 3 Mos before launch |  |  | Existing | [36 empty] | x
| 9.2 |  |  |  | Master Deed & Declaration of Restrictions |  |  | SA | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | Sales Admin |  | 0 | [7 empty] | 39 | 2024-08-08 | 2024-10-01 | [43 empty] | x
[6 empty] | MDDR Drafting & Execution |  | SA | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | Sales Admin |  | 0 |  |  |  | 1 | 2024-08-08 | 2024-08-08 |  | 1 | 2024-08-08 | 2024-08-08 | [6 empty] | Done | [36 empty] | x
[6 empty] | MDDR DHSUD Approval |  | SA | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | Sales Admin |  | 0 |  |  |  | 11 | 2024-09-06 | 2024-09-21 |  | 11 | 2024-09-06 | 2024-09-21 | [6 empty] | Done | [36 empty] | x
[6 empty] | JVA Annotation to Titles |  | SA | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | Sales Admin |  | 0 |  |  |  | 11 | 2024-09-06 | 2024-09-20 |  | 15 | 2024-09-06 | 2024-09-26 | [6 empty] | Done | [36 empty] | x
[6 empty] | MDDR Annotation to Titles |  | SA | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | Sales Admin |  | 0 |  |  |  | 11 | 2024-09-20 | 2024-10-04 |  | 4 | 2024-09-26 | 2024-10-01 | [6 empty] | Done | [36 empty] | x
| 9.3 |  |  |  | Prepare Std Corporate Documents for Buyers for Property Mgt |  |  | SA | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | AOI & By-Laws, Condo Corp, Project Accreditation from Banks | Sales Admin |  | 0 | [7 empty] | 0 | [8 empty] | Existing | [36 empty] | x
| 9.4 |  |  |  | Setup Billing & Collection Process |  |  |  | Collection of PDC for DP; Traking and Reporting of AR ; MIS Setup |  | Sales Admin |  | 0 | [7 empty] | 0 | [5 empty] | 3 Mos before launch |  |  | Existing | [36 empty] | x
2.8 |  |  |  | Develop HR Plan | [6 empty] | HR |  | 34 | 2024-07-01 | 2024-08-15 |  | 0 | 2024-07-01 | 2024-07-01 |  | 1 | 2024-08-30 | 2024-08-30 | [43 empty] | x
| 2.8.1 |  |  |  | Workforce Planning |  |  |  | Develop the Org Structure with Job Profile & Competency Profile. Then populate the Manpower Loading for the whole project consolidating all Dept such as Mktg , Sales, Sales Doc'n , Construction, Finance , Customer Service | Org'n Structure, JP & CP | HR | HR | 34 | 2024-07-01 | 2024-08-15 |  |  | 2024-07-01 | 2024-07-01 |  | 1 | 2024-08-30 | 2024-08-30 | [43 empty] | x
| 2.8.2 |  |  |  | Setup HR & Admin Handbook for the Project |  |  |  | HR & Admin should be tailorfitted to the specifice project with clear Policy and Procedure which include the Timekeeping, Payroll, Office & Site Administrative, Rewards (if there is) | HR & Admin Handbook | HR |  | 24 | 2024-07-15 | 2024-08-15 | [5 empty] | 0 | [8 empty] | Existing | [36 empty] | x
| 2.8.3 |  |  |  | Training Program Plan |  |  |  | Consolidate all the Training Program from Sales, Construction, Customer Service & Property Management . Make sure the this is being performed accordingly by corresponging Dept. | Training Program Plan | HR |  | 0 | [7 empty] | 0 | [8 empty] | Existing | [36 empty] | x
2.9 |  |  |  | Develop Financial Plan |  |  |  |  | Need to create standardized contents for this. Include base, best worst Proposed inclusions: (1) Projected Investment and Funding Sources, (2) Assumptions,(3) Financial Model (projections) - AOP of the Project , Cashflow Statement, Income Statement, Balance Sheet, Scenario Analysis (base, best, worst scenarios), Breakeven analysis, Tax incentives (4) Accounting and Comptrollership - General Acctg, bookkeeping, accounting process and procedures |  |  |  | 241 | 2024-05-01 | 2025-04-02 |  | 699 | 2023-04-19 | 2025-03-18 |  | 241 | 2024-05-01 | 2025-04-02 |  |  | 100% | 6 Mos before launch | [39 empty] | x
| 2.9.1 |  |  |  | Develop the Project Financial Model |  |  |  | FR (Budget), Tax Strategy , Funding Plan | Project Financial Plan | Finance |  | 22 | 2024-05-01 | 2024-05-30 |  | 60 | 2023-04-19 | 2023-07-11 |  | 22 | 2024-05-01 | 2024-05-30 |  |  | 100% | 6 Mos before launch | [39 empty] | x
| 2.9.2 |  |  |  | Setup the Project Accounting Policy & Procedure |  |  |  | Setup of Financial Reporting Structure, Chart of Accts , Guidelines | Project Acctg Manual | Finance |  | 0 |  |  |  | 1 | 2024-05-01 | 2024-05-01 |  | 1 | 2024-05-01 | 2024-05-01 |  |  |  | 6 Mos before launch |  |  | Existing | [36 empty] | x
| 2.9.3 |  |  |  | Setup the ERP System |  |  |  |  | Project ERP System |  |  | 22 | 2024-08-01 | 2024-08-31 |  | 15 | 2024-09-01 | 2024-09-19 |  | 21 | 2024-09-01 | 2024-09-30 |  |  |  | 6 Mos before launch | [39 empty] | x
| 2.9.4 |  |  |  | Bank Accreditation & Funding Plan |  |  |  | Proj Accreditation to Banks & PAG-IBIG, CTS Line, Credit Line, Devt Loan Line | Bank Accredtation, Bank Credit Line, Bank Loans | Sales Admin |  | 131 | 2024-10-02 | 2025-04-02 |  | 120 | 2024-10-02 | 2025-03-18 |  | 131 | 2024-10-02 | 2025-04-02 |  | improve; change to breakdown |  | 4 Mos before Const Comp | [39 empty] | x
2.10 |  |  |  | Develop Customer Service Plan | [8 empty] | 0 | 2024-06-01 | 2024-06-01 |  | 0 | 2024-06-01 | 2024-06-01 |  | 0 | 2024-06-01 | 2024-06-01 | [6 empty] | Existing | [36 empty] | x
2.11 |  |  |  | Develop Work Program
2.12 |  |  |  | Present Project Business Plan |  |  |  |  | Consolidation of all the aspects of plan sucs as the Techn'l, Marketing, Sales, HR & Financials |  |  |  | 63 | 2024-05-21 | 2024-08-15 |  | 117 | 2024-05-21 | 2024-09-15 |  | 426 | 2024-05-21 | 2026-01-06 | [43 empty] | x
| 2.12.1 |  |  |  | Crafting of Business Plan Paper |  |  |  | Proj Accreditation to Banks & PAG-IBIG, CTS Line, Credit Line, Devt Loan Line | Bank Accredtation, Bank Credit Line, Bank Loans | Sales Admin |  | 26 | 2024-07-01 | 2024-08-05 |  | 45 | 2024-07-01 | 2024-08-30 |  | 49 | 2024-07-01 | 2024-09-05 |  |  |  | 4 Mos before Const Comp |  |  | ongoing | [36 empty] | x
| 2.12.2 |  |  |  | Presentation to Management |  |  |  | Proj Accreditation to Banks & PAG-IBIG, CTS Line, Credit Line, Devt Loan Line | Bank Accredtation, Bank Credit Line, Bank Loans | Sales Admin |  | 1 | 2024-05-21 | 2024-05-21 |  | 117 | 2024-05-21 | 2024-09-15 |  | 1 | 2024-05-21 | 2024-05-21 |  |  |  | 4 Mos before Const Comp |  |  | done | [36 empty] | x
|  | 2.12.1 |  |  |  | Initial Presentation |  |  | Proj Accreditation to Banks & PAG-IBIG, CTS Line, Credit Line, Devt Loan Line | Bank Accredtation, Bank Credit Line, Bank Loans | Sales Admin |  | 1 | 2024-08-15 | 2024-08-15 |  | 1 | 2024-05-21 | 2024-05-21 |  | 1 | 2024-05-21 | 2024-05-21 |  |  |  | 4 Mos before Const Comp | [39 empty] | x
|  | 2.12.2 |  |  |  | Full Business Plan Presentation (GGA) |  |  | Proj Accreditation to Banks & PAG-IBIG, CTS Line, Credit Line, Devt Loan Line | Bank Accredtation, Bank Credit Line, Bank Loans | Sales Admin |  | 1 | 2024-08-15 | 2024-08-15 |  | 1 | 2024-09-04 | 2024-09-04 |  | 1 | 2024-09-09 | 2024-09-09 |  |  |  | 4 Mos before Const Comp | [39 empty] | x
|  | 2.12.3 |  |  |  | Full Business Plan Presentation (ESA) |  |  | Proj Accreditation to Banks & PAG-IBIG, CTS Line, Credit Line, Devt Loan Line | Bank Accredtation, Bank Credit Line, Bank Loans | Sales Admin |  | 1 | 2024-08-15 | 2024-08-15 |  | 1 | 2024-09-11 | 2024-09-11 |  | 1 | 2024-10-08 | 2024-10-08 |  |  |  | 4 Mos before Const Comp |  |  | Second Pass | [36 empty] | x
|  | 2.12.4 |  |  |  | Presentation to Board |  |  | Proj Accreditation to Banks & PAG-IBIG, CTS Line, Credit Line, Devt Loan Line | Bank Accredtation, Bank Credit Line, Bank Loans | Sales Admin |  | 1 | 2024-08-15 | 2024-08-15 |  | 1 | 2024-09-08 | 2024-09-08 |  | 1 | 2024-10-22 | 2024-10-22 |  |  |  | 4 Mos before Const Comp |  |  | for confirmation of schedule | [36 empty] | x
|  | 2.12.5 |  |  |  | Presentation to JV Partner |  |  | Proj Accreditation to Banks & PAG-IBIG, CTS Line, Credit Line, Devt Loan Line | Bank Accredtation, Bank Credit Line, Bank Loans | Sales Admin |  | 1 | 2024-08-15 | 2024-08-15 |  | 1 | 2024-09-15 | 2024-09-15 |  | 1 | 2024-10-23 | 2024-10-23 |  |  |  | 4 Mos before Const Comp | [39 empty] | x
| 13.4 |  |  |  | Secure Approval (with Comments) |  |  |  | Proj Accreditation to Banks & PAG-IBIG, CTS Line, Credit Line, Devt Loan Line | Bank Accredtation, Bank Credit Line, Bank Loans | Sales Admin |  | 1 | 2024-06-25 | 2024-06-25 |  | 0 | 2024-06-25 | 2024-06-25 |  | 1 | 2024-06-25 | 2024-06-25 |  |  |  | 4 Mos before Const Comp |  |  | done | [36 empty] | x
| 13.5 |  |  |  | Launch Memo |  |  |  | Proj Accreditation to Banks & PAG-IBIG, CTS Line, Credit Line, Devt Loan Line | Bank Accredtation, Bank Credit Line, Bank Loans | Sales Admin |  | 1 | 2024-07-30 | 2024-07-30 |  | 0 | 2024-08-19 | 2024-08-19 |  | 362 | 2024-08-19 | 2026-01-06 |  |  |  | 4 Mos before Const Comp |  |  | done - pending implementation | [36 empty] | x
|  |  | EXECUTION & MONITORING PHASE | [9 empty] | 118 | 2024-03-20 | 2024-08-30 |  |  | 2024-03-19 | #REF! |  | #REF! | 2024-05-19 | #REF! |  |  | #DIV/0! | [40 empty] | x
14 |  |  |  | Showroom | [8 empty] | #REF! | 2024-03-20 | #REF! |  | #REF! | 2024-03-19 | #REF! |  | 205 | 2024-05-19 | 2025-03-01 |  |  | #DIV/0! | [40 empty] | x
| 14.1 |  |  |  | Secure Showroom Location |  |  |  |  | Running Ads |  |  | 2 | 2024-03-19 | 2024-03-20 |  | 2 | 2024-03-19 | 2024-03-20 |  | 69 | 2024-02-13 | 2024-05-19 | [6 empty] | for proposal of lease rate and negotiation of final showroom location layout | [36 empty] | x
[6 empty] | Lease Rates Negotiation | [14 empty] | 58 | 2024-05-19 | 2024-08-07 | [6 empty] | final rates ok | [36 empty] | x
[6 empty] | Lease Agreement Finalization | [14 empty] | 7 | 2024-08-07 | 2024-08-15 | [6 empty] | signing sept 12 | [36 empty] | x
| 14.1 |  |  |  | Showroom Design |  |  |  |  | Running Ads |  |  | 30 | 2024-03-20 | 2024-04-30 |  | 30 | 2024-03-20 | 2024-04-30 |  | 60 | 2024-05-19 | 2024-08-09 | [43 empty] | x
[6 empty] | FCD |  |  |  | Running Ads |  |  | 23 | 2024-03-20 | 2024-04-20 |  | 23 | 2024-03-20 | 2024-04-20 |  | 52 | 2024-05-19 | 2024-07-30 | [6 empty] | ongoing with MCC already | [36 empty] | x
[6 empty] | Costing |  |  |  | Running Ads |  |  | 7 | 2024-04-20 | 2024-04-30 |  | 7 | 2024-04-20 | 2024-04-30 |  | 9 | 2024-07-30 | 2024-08-09 | [43 empty] | x
| 14.2 |  |  |  | Showroom Permits |  |  | M | Event Preparation up to event execution | Event |  |  | 22 | 2024-03-22 | 2024-04-22 |  | 22 | 2024-03-22 | 2024-04-22 |  | 150 | 2024-07-30 | 2025-02-24 | [43 empty] | x | bar: 2024-03-31
[6 empty] | Barangay Permit |  | M | Event Preparation up to event execution | Event |  |  | 11 | 2024-03-22 | 2024-04-06 |  | 11 | 2024-03-22 | 2024-04-06 |  | 14 | 2024-07-30 | 2024-08-16 | [6 empty] | secured | [36 empty] | x | bar: 2024-03-31
[6 empty] | Building Permit |  | M | Event Preparation up to event execution | Event |  |  | 22 | 2024-03-22 | 2024-04-22 |  | 22 | 2024-03-22 | 2024-04-22 |  | 95 | 2024-09-09 | 2025-01-17 |  | delayed |  |  |  |  | MCC to provide lacking docs; need lease agreement | [36 empty] | x | bar: 2024-03-31
[6 empty] | Occupancy Permit |  | M | Event Preparation up to event execution | Event |  |  | 0 |  |  |  | 0 |  |  |  | 18 | 2025-01-30 | 2025-02-24 |  | based on best case projection | [41 empty] | x
| 14.2 |  |  |  | Tender Process/Awarding |  |  | M | Event Preparation up to event execution | Event |  |  | 11 | 2024-05-01 | 2024-05-15 |  | 11 | 2024-05-01 | 2024-05-15 |  | 4 | 2024-08-10 | 2024-08-15 | [6 empty] | Done | [36 empty] | x | bar: 2024-04-30 to 2024-05-31
| 14.3 |  |  |  | Showroom Construction |  |  | M | ??? |  |  |  | 67 | 2024-05-30 | 2024-08-30 |  | 67 | 2024-05-30 | 2024-08-30 |  | 105 | 2024-10-05 | 2025-03-01 |  | best case projection |  |  |  |  | October Day 1 based on EPC submitted work program | 92 | [35 empty] | x
[6 empty] | Soft Mobilization |  | M | ??? |  |  |  | 67 | 2024-05-30 | 2024-08-30 | [5 empty] | 0 | 2024-10-05 | 2024-10-05 | [43 empty] | x
[6 empty] | Tree Cutting & Site Clearing |  | M | ??? |  |  |  | 67 | 2024-05-30 | 2024-08-30 | [5 empty] | 4 | 2024-10-09 | 2024-10-14 | [6 empty] | ongoing | [36 empty] | x
[6 empty] | Structural Works |  | M | ??? |  |  |  | 67 | 2024-05-30 | 2024-08-30 | [5 empty] | 68 | 2024-10-14 | 2025-01-15 | [43 empty] | x
[6 empty] | Basic Architectural Works | [6 empty] | 67 | 2024-05-30 | 2024-08-30 | [5 empty] | 33 | 2025-01-15 | 2025-03-01 | [43 empty] | x
[6 empty] | Site Development Works | [6 empty] | 67 | 2024-05-30 | 2024-08-30 | [5 empty] | 35 | 2024-11-03 | 2024-12-22 | [43 empty] | x
[6 empty] | Carwash Removal | [6 empty] | 67 | 2024-05-30 | 2024-08-30 | [5 empty] | 12 | 2025-01-15 | 2025-01-30 | [43 empty] | x
| 14.4 |  |  |  | Showroom Furnishing (FF&E) |  |  |  | Hiring & Accreditation | Employee Hires |  |  | 23 | 2024-07-31 | 2024-08-30 |  | 23 | 2024-07-31 | 2024-08-30 |  | 22 | 2025-01-30 | 2025-03-01 |  |  |  | 6 Mos before LTS release (SD) 4 Mos Before LTS release (SM) 3 Mos before LTS release (PS) | [39 empty] | x
| 14.5 |  |  |  | Showroom Operational Requirements (Admin) |  |  |  | Training | Sales Platform Knowledge |  |  | 23 | 2024-07-31 | 2024-08-30 |  | 23 | 2024-07-31 | 2024-08-30 |  | 22 | 2025-01-30 | 2025-03-01 |  |  |  | 5 Mos before soft launch | [39 empty] | x
15 |  |  |  | Pre Launch | [8 empty] | #REF! | #REF! | #REF! |  | 1899-12-31 | #REF! | #REF! |  | 120 | 2024-05-29 | 2024-11-12 |  |  | #DIV/0! | [40 empty] | x
| 15.1 |  |  |  | Social Media Campaign |  |  |  | Opening of social media accounts and boosting of ads for the project lifetime. | Running Ads | Mktg |  | #REF! | #REF! | #REF! |  | 1 | #REF! | #REF! |  | 43 | 2024-08-01 | 2024-09-30 | [43 empty] | x
[6 empty] | Digital Teaser Ads | [6 empty] | 1 | 2024-05-29 | 2024-05-29 | [5 empty] | 16 | 2024-08-23 | 2024-09-15 | [43 empty] | x
| 15.2 |  |  |  | Ground Breaking Event* |  |  | M | Event Preparation up to event execution | Event | Mktg |  | 1 | 2024-05-29 | 2024-05-29 |  | 1 | 2024-05-29 | 2024-05-29 |  | 1 | 2024-05-29 | 2024-05-29 | [43 empty] | x | bar: 2024-04-30 to 2024-05-31
| 15.3 |  |  |  | Pre Launch Sales* |  |  | M | ??? |  | Sales | HR | 0 | 2024-06-15 | 2024-06-15 |  | 1 | 2024-06-15 | 2024-06-15 |  | 90 | 2024-07-10 | 2024-11-12 | [43 empty] | x | bar: 2024-05-31 to 2024-06-30
| 15.4 |  |  |  | Sales Hiring/Broker Accreditation |  |  |  | Hiring & Accreditation | Employee Hires | Sales | HR | 22 | 2024-05-16 | 2024-06-15 |  | 30 | 2024-05-16 | 2024-06-15 |  | 24 | 2024-07-15 | 2024-08-15 |  |  |  | 6 Mos before LTS release (SD) 4 Mos Before LTS release (SM) 3 Mos before LTS release (PS) | [39 empty] | x
| 15.5 |  |  |  | Sales Training/NOAH |  |  |  | Training | Sales Platform Knowledge | Sales | HR | 22 | 2024-05-16 | 2024-06-15 |  | 30 | 2024-05-16 | 2024-06-15 |  | 12 | 2024-08-15 | 2024-08-30 |  |  |  | 5 Mos before soft launch | [39 empty] | x
| 15.6 |  |  |  | Project Briefing & Orientation |  |  |  | PKS | Sales project Knowledge | Sales | HR | 22 | 2024-05-16 | 2024-06-15 |  | 30 | 2024-05-16 | 2024-06-15 |  | 35 | 2024-07-15 | 2024-08-30 | [43 empty] | x
| 15.7 |  |  |  | LOI Implementation |  |  |  | LOI Ececution | Number of LOI's | Sales | HR | #REF! | 2024-06-15 | #REF! |  | 60 | 2024-06-15 | 2024-08-14 |  | 90 | 2024-07-10 | 2024-11-12 |  |  |  | LOI period 3 Mos before launch | [39 empty] | x
3 |  |  |  | Project Launch | [8 empty] | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | [43 empty] | x
| 3.1 |  |  |  | Execute Marketing Plan
| 16.1.1 |  |  |  | Digital Launch Ads |  |  |  | Live/Release of Digital Materials ????? | Social Media Materials, Website | Mktg |  | 0 | [5 empty] | 0 |  | 1 | 2024-10-01 | 2024-10-01 | [43 empty] | x
| 16.1.2 |  |  |  | Lamudi Webilaunch* |  |  | M | Event Preparation up to event execution | Webilaunch Event | Mktg |  | 0 | [5 empty] | 0 |  | 0 | [45 empty] | x
| 16.1.3 |  |  |  | Press/ Media Release |  |  |  | Press & Media release should be planned in Calendar for the period of whole project | PR | Mktg |  | 0 | [5 empty] | 0 |  | 5 | 2024-10-01 | 2024-10-07 | [43 empty] | x
| 16.1.4 |  |  |  | Launch Event* |  |  | M | Event Prep up to Event Execution | Launch Event* | Mktg | Sales | #REF! | #REF! | #REF! |  | 0 | 2024-09-15 | 2024-09-15 |  | 1 | 2024-10-15 | 2024-10-15 |  |  |  | 3 Mos before launch |  |  | finalize date | [36 empty] | x | bar: 2024-08-31 to 2024-09-30
| 16.1.5 |  |  |  | First Open House* |  |  | M | Event Prep up to Event Execution | Open House* | Sales | Mktg | #REF! | #REF! | #REF! |  | 0 | 2024-09-07 | 2024-09-07 |  | 0 | 2024-12-07 | 2024-12-07 | [6 empty] | check showroom operational day 1 | [36 empty] | x | bar: 2024-08-31 to 2024-09-30
| 16.1.6 |  |  |  | LOI Sales Conversion |  |  |  | Conversion of LOI sold during the Pre-Launch with a given period of ?? Days. | Sales Conversion | Sales |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | [43 empty] | x
| 16.1.7 |  |  |  | Email/Text Network Blasting |  |  |  | This should be planned and executed periodically | Customers Leads | Sales |  | 0 | [5 empty] | 0 |  | 0 | [45 empty] | x
| 16.1.8 |  |  |  | Sales Calls & Networking |  |  |  | Sourcing of leads should be planned in a Calendar in multiple initiatives that include Road Shows , Corporate Sales Call etc. | Customers Leads | Sales |  | 0 | [5 empty] | 0 |  | 0 | [45 empty] | x
| 16.1.9 |  |  |  | Sales Presentation & Tripping ? |  |  |  | Client Presentations | Customers Leads | Sales |  | 0 | [5 empty] | 0 |  | 0 | [45 empty] | x
| 16.1.10 |  |  |  | Sales Media Bossting |  |  |  | From LOI to reservation. | Customers Leads | Sales |  | 0 | [5 empty] | 0 |  | 0 | [5 empty] | Upon release of LTS | [39 empty] | x
| 3.2 |  |  |  | Execute Sales Plan
| 3.3 |  |  |  | Fundraising Activities
x |  |  |  | Project Funding | [6 empty] | Diana |  | 1629 | 2025-02-01 | 2031-05-01 |  | 0 |  |  |  | 0 |  |  |  |  | #DIV/0! | [40 empty] | x
| x |  |  |  | Kick-Off with Banks for Development Loan | [5 empty] | Diana |  | 21 | 2025-02-01 | 2025-03-03 |  | 0 |  |  |  | 21 | 2024-11-15 | 2024-12-15 |  | confirm steps with corpfin |  | SD1 | [39 empty] | x
| x |  |  |  | Presentations & Negotiations |  |  |  | Tender Process include from (1) Pre-Qualifications (2) Issue of Tender Docs (3) Receipt and Review of Tenders (4) Negotiations and Award of Contract. The Tender documents are the (1) Terms of Reference, (2) Scope of Work (BoQ), (3) Construction Program (Project Schedule) (4) Construction Drawings , (5) Material Specidications and (6) Construction Contract . | Conctruciton Documentation | Diana |  | 1 | 2025-03-03 | 2025-03-03 |  | 0 |  |  |  | 56 | 2024-12-15 | 2025-03-03 |  |  |  | SD1 | [39 empty] | x
| x |  |  |  | Development Loan Contract Signing |  |  |  | Tender Process include from (1) Pre-Qualifications (2) Issue of Tender Docs (3) Receipt and Review of Tenders (4) Negotiations and Award of Contract. The Tender documents are the (1) Terms of Reference, (2) Scope of Work (BoQ), (3) Construction Program (Project Schedule) (4) Construction Drawings , (5) Material Specidications and (6) Construction Contract . | Conctruciton Documentation | Diana |  | 1 | 2025-03-03 | 2025-03-03 |  | 0 |  |  |  | 1 | 2025-03-03 | 2025-03-03 |  |  |  | SD1 | [39 empty] | x
| x |  |  |  | First Drawdown* |  |  |  | Conduct kick-off meeting together with the Contractors to define the Communication Schedules and Stakeholders . | Minutes of Meeting; Meeting Schedules | Diana |  | 1 | 2025-05-02 | 2025-05-02 |  | 0 |  |  |  | 1 | 2025-05-02 | 2025-05-02 | [43 empty] | x
4 |  |  |  | Construction | [6 empty] | Diana |  | 1629 | 2025-02-01 | 2031-05-01 |  | 0 | 2031-05-01 | 2033-11-01 |  | 1609 | 2025-03-03 | 2031-05-01 |  |  | #DIV/0! | [40 empty] | x
| 4.1 |  |  |  | Organize Construction Management Team | [5 empty] | Diana |  | 21 | 2025-02-01 | 2025-03-03 |  | 1 | 2025-03-03 | 2025-03-03 |  | 1 | 2025-03-03 | 2025-03-03 |  |  |  | SD1 | [39 empty] | x
| 4.1 |  |  |  | Detailed Engineering Plan
| 4.1 |  |  |  | Develop Construction Plan
| 4.1 |  |  |  | Construction Performance Review
| 17.2 |  |  |  | Tender Process |  |  |  | Tender Process include from (1) Pre-Qualifications (2) Issue of Tender Docs (3) Receipt and Review of Tenders (4) Negotiations and Award of Contract. The Tender documents are the (1) Terms of Reference, (2) Scope of Work (BoQ), (3) Construction Program (Project Schedule) (4) Construction Drawings , (5) Material Specidications and (6) Construction Contract . | Conctruciton Documentation | Diana |  | 1 | 2025-03-03 | 2025-03-03 |  | 1 | 2025-03-03 | 2025-03-03 |  | 1 | 2025-03-03 | 2025-03-03 |  |  |  | SD1 | [39 empty] | x
| 17.4 |  |  |  | Project Kick- Off * |  |  |  | Conduct kick-off meeting together with the Contractors to define the Communication Schedules and Stakeholders . | Minutes of Meeting; Meeting Schedules | Diana |  | 1 | 2025-05-02 | 2025-05-02 |  | 1 | 2025-05-02 | 2025-05-02 |  | 1 | 2025-05-02 | 2025-05-02 | [43 empty] | x
| 17.5 |  |  |  | Commencement * |  |  |  | Conmencement date of construction | na | Diana |  | 0 | 2025-06-01 | 2025-06-01 |  | 0 | 2025-06-01 | 2025-06-01 |  | 0 | 2025-06-01 | 2025-06-01 | [43 empty] | x
| 17.6 |  |  |  | Top-Off* |  |  |  | Last Pouring of Concrete , signifying the completion of the Structural Works. This normally comes with an event of Toping Off Ceremony with Mktg and Sales Team of the project . | na | Diana |  | 458 | 2027-06-01 | 2029-03-01 |  | 1 | 2029-03-01 | 2029-03-01 |  | 458 | 2027-06-01 | 2029-03-01
| 17.7 |  |  |  | Handover of Resd'l Units fr Contractor |  |  |  | This is the start of the completion of First Residential Units with complete functional testing and punh list close out . The handover will be from Contractor to Developer . At this stage , the Units can be presented to the Bank for the Bank User Take-Out . | Handover Form (per Unit) | Diana |  | 22 | 2028-12-01 | 2029-01-01 |  | 24 | 2029-01-01 | 2029-02-01 |  | 22 | 2028-12-01 | 2029-01-01
| 17.8 |  |  |  | Final Testing & Commissioning |  |  |  | The final Testing & Commissioning of the main system which include the Mechanical , Electrical , Plumbin & Fire Protection which will be presented by Contractor to Developer and to be witnessed by Property Administration . | Certificate of Testing & Commissioning | Diana |  | 652 | 2028-11-01 | 2031-05-01 |  | 654 | 2031-05-01 | 2033-11-01 |  | 652 | 2028-11-01 | 2031-05-01
| 17.9 |  |  |  | Final Handover * |  |  |  | This is the Final Acceptance of the Construction to be handed over to the Property Mgt | Certificate of Final Acceptance | Ops / Technical |  | 0 |  |  |  | 0 |  |  |  | 0 | [45 empty] | x
5 |  |  |  | Construction Commisioning & Handover
| 5.1 |  |  |  | Set up of Property Management Organization
| 5.2 |  |  |  | Testing and Commisioning
| 5.3 |  |  |  | Acceptance of Handover Units from Contractor
| 5.4 |  |  |  | Handover of Units to Property Management
| 18.1 |  |  |  | Property Management Team
| 18.2 |  |  |  | T&C Report
| 18.3 |  |  |  | Signed Unit Inspection Form
| 18.4 |  |  |  | COCA from Property Management
6 |  |  |  | End-User Financing/Take-Out | [6 empty] | Sales Admin |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | #DIV/0! | 3 Mos before Const Comp | [39 empty] | x
| 6.1 |  |  |  | Project Accreditation to Bank & HDMF
| 6.2 |  |  |  | Completion of Bank Docs of the Buyers |  |  |  |  | Customer Folder | Sales Admin |  | 0 | [5 empty] | 0 |  | 0 | [5 empty] | 7 Mos before Const Comp | [39 empty] | x
| 6.3 |  |  |  | Bank/Pag-IBIG Take-out | [5 empty] | Sales Admin |  | 0 | [5 empty] | 0 |  | 0 | [5 empty] | 3 Mos after Const Comp | [39 empty] | x
| 6.4 |  |  |  | TCT and Tax Dec. Transfer to Buyers |  |  |  |  | TCT | Sales Admin |  | 0 | [5 empty] | 0 |  | 0 | [5 empty] | 6 Mos after const comp | [39 empty] | x
19 |  |  |  | Property Management Setup | [8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | #REF! | [40 empty] | x
| 19.1 |  |  |  | Setup of Property Mgt Org'n | [5 empty] | Ops / Technical |  | 0 | [5 empty] | 0 |  | 0 | [5 empty] | 6 mo before const comp | [39 empty] | x
| 19.2 |  |  |  | Handover of Resd' Units to Owners | [7 empty] | 0 | [5 empty] | 0 |  | 0 | [45 empty] | x
|  |  | CLOSE OUT PHASE | [9 empty] | #REF! | 0 | #REF! |  | 0 | #REF! | 0 |  | #REF! | 0 | #REF! |  |  | #DIV/0! | [40 empty] | x
7 |  |  |  | Property Mgt & Community Relations | [8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | #DIV/0! | [40 empty] | x
| 7.1 |  |  |  | Handover of Units to Owners
| 7.2 |  |  |  | Set up of Operations and Maintenance | [7 empty] | 0 | [5 empty] | 0 |  | 0 | [5 empty] | Upon turnover of bldg to PMO | [39 empty] | x
| 7.3 |  |  |  | Setting up of HOA and Condo Corp. |  |  |  | Handover of the whole property (amenities, towers, etc. |  |  |  | 0 | [5 empty] | 0 |  | 0 | [5 empty] | 6 mo before const comp | [39 empty] | x
8 |  |  |  | Project Close out | [8 empty] | #REF! | 0 | #REF! |  | 0 | #REF! | 0 |  | #REF! | 0 | #REF! |  |  | #DIV/0! | [40 empty] | x
| 8.1 |  |  |  | Construction Close-out
| 8.2 |  |  |  | Employees Transfer | [7 empty] | 0 | [5 empty] | 0 |  | 0 | [5 empty] | 3 mos after selling period | [39 empty] | x
| 8.3 |  |  |  | Project Financial Close-out | [7 empty] | 0 | [5 empty] | 0 |  | 0 | [45 empty] | x
| 8.4 |  |  |  | Documentation Archiving |  |  |  |  | Folders, Plans, Licences, Permits |  |  | 0 | [5 empty] | 0 |  | 0 | [45 empty] | x
| 8.5 |  |  |  | Regulatory and Legal | [7 empty] | 0 | [5 empty] | 0 |  | 0 | [45 empty] | x
x | x | x | x | x | x | x | x |  | x | x | x |  | x | x | x | x | x | x | x | x | x | x | x | x |  | x | x | x | x |  | x | [35 empty] | x | bar: 2023-03-31 to 2026-01-31
NOTES :
|  |  | * | Milestones . There is only one date (No Finish Date)
Include Showroom Line Item
Formulas:
Monthly = [Monthly, row above]
Monthly = MIN([Monthly, row below]:T33)
Gantt view = NETWORKDAYS([Monthly],U29)
Gantt view = MIN([Gantt view, row below]:S113)
Note on Q20: ====== ID#AAABfPAIkVY tc={3707FD58-284F-5C41-B0CE-AAC87CA0D8AF} (2025-03-24 10:44:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: delayed from Jan 29 original pegged
Note on Y20: ====== ID#AAABfPAIkVA tc={7220F4DE-740D-E741-9BA0-C842156541AA} (2025-03-24 10:44:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: delayed from Jan 29 original pegged
Note on Q35: ====== ID#AAABfPAIkVE tc={F896E7E8-3DFD-FF47-8908-CBBDCBCE26B7} (2025-03-24 10:44:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: tentative earliest Reply: delayed due to podium options; initial A3 plans already submitted for Barangay Permit
Note on U35: ====== ID#AAABfPAIkVQ tc={2AAF86B8-E59D-2849-8F41-186D36535F30} (2025-03-24 10:44:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: tentative earliest Reply: delayed due to podium options; initial A3 plans already submitted for Barangay Permit
Note on Y35: ====== ID#AAABfPAIkVk tc={E4301399-CA65-DA42-8A88-3ECF74227C7B} (2025-03-24 10:44:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: tentative earliest Reply: delayed due to podium options; initial A3 plans already submitted for Barangay Permit
Note on P43: ====== ID#AAABfPAIkVc tc={51ECB6E1-FB79-AB4A-8D26-9041EA1804F7} (2025-03-24 10:44:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: High impact on TLS. Feb 12 start of compilation of requirements
Note on T43: ====== ID#AAABfPAIkVI tc={7D9377B7-73CC-4F41-856D-35B16C583AFF} (2025-03-24 10:44:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: High impact on TLS. Feb 12 start of compilation of requirements
Note on X43: ====== ID#AAABfPAIkVM tc={CBD84899-4115-7542-B3AF-F172BA802B3B} (2025-03-24 10:44:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: High impact on TLS. Feb 12 start of compilation of requirements
Note on Q90: ====== ID#AAABfPAIkVg tc={277B9408-E958-4248-AEDA-61C0B55068C9} (2025-03-24 10:44:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: adjust accordingly
Note on U90: ====== ID#AAABfPAIkVU tc={E227BF6C-F80F-A54B-AFD6-CBF81C9A47D9} (2025-03-24 10:44:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: adjust accordingly

## Glossary of Terms
GLOSSARY OF TERMS
No. | Term | Definition
1 | No | No refers to the WBS or activity coding which is unique for each WBS or Activity.
2 | Activity | This is the column for the WBS or Activity names.
3 | Description | A statement or account giving the characteristics of the Activity or WBS.
4 | Output | This descibes the output/result for each activity it may be a document or thers.
5 | Responsible Person | The person who has control or is incharge over the activity and who needs to make sure that the project reaches completion.
| Support Person | The person who will assist or provide backing for the Responsible Person.
6 | % of Completion | Amount of work completed in terms of percentage.
7 | Predecessors | A required prior task or an activity that must be started or completed before another activity can begin or be completed.
8 | Start | The start date of the activity.
9 | Finish | The completion date of the activity.
10 | Duration | This is the target time in days to complete the activity.
11 | Type | This column categorizes each entry as an Activity, Sub-Activity, or Milestone to define its role within the project.
11.1 | Activity Type (A) | Activities represent major tasks.
11.2 | Sub Activity Type (SA) | Sub-Activities break Activities down into smaller steps.
11.3 | Milestone Type (M) | Milestones mark significant progress points.
12 | Baseline 0 (BL0) | The initial approved project schedule, serving as a reference for tracking progress, comparing planned vs. actual performance.
13 | Baseline 1 (BL1) | Revised project schedule, reflecting approved changes and serving as a new tracking reference.
14 | Running | Project progress.
15 | L1 | This pertains to the Phase in the framework.
16 | L2 | This pertains to the Activity in the framework. The Activity # in the Work Program should match the Activity # in the Framework
17 | L3 | This pertains to the Sub-Activity in the framework
18 | L4 | This pertains to the Detailed Activity in the framework, under the Sub-Activity.
RASCI MATRIX
No. | Term | Definition
R | Responsible | ● Who needs to make sure that the project reaches completion? ● There can be no more than one task owner. ● This appears as "prepared by" in the document / file.
A | Accountable | ● Who has ultimate control over the project and its resources? ● There can be no more than one person accountable. ● This appears as "approved by" in the document / file.
S | Support | ● Who will provide help to responsible members? ● This is a required (or must) support task to the Responsible person in completing the work/ activity. ● This appears as "noted by" in the document / file to be signed off.
C | Consulted | People who provide information for the project and with whom there is two-way communication. This can be several people, often subject matter experts. This person is not required to be part of the team to complete the task of the Responsible person, but rather an option (as needed basis) to the responsible
I | Informed | People or stakeholders who need to be kept "in the picture." They need updates on progress or decisions, but they do not need to be formally consulted, nor do they contribute directly to the task or decision.

## TEAM
Vendor / Developer's Team |  |  | Client's Team
Roles | Description | Abbreviation | Roles | Description | Abbreviation
Partner Project Manager | Oversees project delivery from vendor side, manages schedule, scope, and client coordination. | PPM | Customer Project Manger (CPM) | Leads the project from the customer side, manages timelines, resources, and communication with the vendor. | FIN
Partner Functional Consultant | Gathers and interprets client requirements, creates business logic and workflow designs. | PFC | Customer Business Process Leads (CBPL) | Owns specific business areas, defines processes, validates design, and ensures solution meets business needs. | FIN/IT/COM
Partner Technical Support | Handles environment setup, deployment support, and infrastructure coordination. | PTS | Customer Technical Team Member (CTTM) | Handles technical tasks like integration, data migration, and system setup in coordination with the vendor. | IT
|  |  | Customer Business Process Member (CBPM) | Supports process leads by providing operational input, assisting in testing, training, and documentation. | FIN/IT/COM